## Progress
Functionality | Task | Summary | Description | Est Start | Start Date | End Date | Status | Notes
Project Setup |  |  |  |  | 2025-02-20 | 2025-02-20 | done
Data Import and Initialization | Import file |  |  |  | 2025-02-20 | 2025-02-21 | done
| Channel signal retrieval |  |  |  | 2025-02-28 | 2025-02-28 | done
| Downsampling |  |  |  | 2025-02-21 | 2025-03-02 | done
Result Compare | Save read data to csv(MATLAB) |  | Save data in each step |  | 2025-02-21 | 2025-02-21 | done
| Compare Data | compare with imported file data for testing | Test the C program by comparing result of MATLAB and C program, throw error when not the same |  | 2025-02-21 | 2025-02-21 | done
Preprocessing Stage | Low-Pass & High-Pass Filtering | Remove noise while preserving slow waves. | Removes high-frequency noise and baseline drift. Uses FIR filters for smooth processing. | 2025-03-03 | 2025-03-03 |  | ongoing
| Artifact Detection & Removal | Clean the signal from artificial stimulation effects. | artifact_detect.m: Detects artifacts by finding extreme values. artifact_remove.m: Removes detected artifacts and replaces them with cubic spline interpolation. | 2025-03-06
Feature Extraction | Non-Linear Energy Operator (NEO) | Highlight activation points. | Enhances sudden energy changes in the signal. Helps detect slow wave activations. | 2025-03-10
| Edge Detection | Enhance slow wave activation points. | Detects sharp drops in the signal (which correspond to slow wave activations). Uses a convolution kernel [1, 0, -1] to find steep slopes. | 2025-03-13
Activation Detection | Thresholding | Detect valid slow wave activations while ignoring noise. | A dynamic threshold is used to mark slow wave activations. | 2025-03-17
Post-Processing | Duplicate Removal | Ensure one activation per cycle. | Removes duplicate detections within 500 samples (since slow waves are ~20 sec apart). Prevents false positives due to signal fluctuations. | 2025-03-20
Testing and Refactoring |  |  |  | 2025-03-24