## Progress
Functionality | Task | Summary | Description | Est Start | Start Date | End Date | Status | Notes
Project Setup |  |  |  |  | 2025-02-20 | 2025-02-20 | done
Data Import and Initialization | Import file |  |  |  | 2025-02-20 | 2025-02-21 | done
| Channel signal retrieval |  |  |  | 2025-02-28 | 2025-02-28 | done
| Downsampling |  |  |  | 2025-02-21 | 2025-03-02 | done
Result Compare | Save read data to csv(MATLAB) |  | Save data in each step |  | 2025-02-21 | 2025-02-21 | done
| Compare Data | compare with imported file data for testing | Test the C program by comparing result of MATLAB and C program, throw error when not the same |  | 2025-02-21 | 2025-02-21 | done
Preprocessing Stage | Low-Pass & High-Pass Filtering | Remove noise while preserving slow waves. | Removes high-frequency noise and baseline drift. Uses FIR filters for smooth processing. | 2025-03-03 | 2025-03-03 | 2025-03-14 | done | May need to adjust later. Currently copied wrong logic in Daryl's project to get same results. Also the result have a average difference of 3.64e-11 compared to the daryl's results. Largest diffence was 1e-8. PERCISION constant of PRECISION to 1e-8
| Artifact Detection & Removal | Clean the signal from artificial stimulation effects. | artifact_detect.m: Detects artifacts by finding extreme values. artifact_remove.m: Removes detected artifacts and replaces them with cubic spline interpolation. | 2025-03-06 | 2025-03-14 | 2025-03-18 | done | Changed PRECISION to 1e-7 because the max diff between matlab and C increased
Feature Extraction | Non-Linear Energy Operator (NEO) | Highlight activation points. | Enhances sudden energy changes in the signal. Helps detect slow wave activations. | 2025-03-10 | 2025-03-18 | 2025-03-18 | done | Changed PRECISION to 1e-6 because the max diff between matlab and C increased.
| Max Average Filtering |  |  |  | 2025-03-18 | 2025-03-18 | done
| Edge Detection | Enhance slow wave activation points. | Detects sharp drops in the signal (which correspond to slow wave activations). Uses a convolution kernel [1, 0, -1] to find steep slopes. | 2025-03-13
Activation Detection | Thresholding | Detect valid slow wave activations while ignoring noise. | A dynamic threshold is used to mark slow wave activations. | 2025-03-17
Post-Processing | Duplicate Removal | Ensure one activation per cycle. | Removes duplicate detections within 500 samples (since slow waves are ~20 sec apart). Prevents false positives due to signal fluctuations. | 2025-03-20
Testing and Refactoring |  |  |  | 2025-03-24

## Journal
Low Pass Filtering functionality in C | 2025-03-07 | It took alot of time attempting to understand the filtering logic, especially due to Daryl's MATLAB project used a built in MATLAB lowpass function. It was not clear what coefficient was used in this function, but there was a file called lowpass_coeffs.mat in the root directory of the project, but was not imported in any part of the project code. I assumed somehow it was an extracted coefficient of the whats used in the lowpass function so used is in my C low pass filtering functionality. I got a similar trend of result comparing with the matlab code(shown in diagram, but C showing results of about 150 higher that the MATLAB results. | #VALUE!
|  | I got it to get similar result but not exactly the same. I think it may be because I am using floats instead of double in my C code, Matlab uses double. Plan to change to double next | #VALUE!
| 2025-03-12 | Figured out the problem from deeply investigating the daryl's MATLAB project's lowpass filter logic and reading documentations of how the built in filter() function works. Found out the following. 1. In Daryl's code layer - 60 padding front and back added to signal(first value for front 600 values and end value for back 60 values) - then it is passed to built in lowpass function - then the paddings are removed front and back from the output signal from the lowpass function 2. MATLAB Layer - built in lowpass function checks the opts variables and runs FIR logic, which firstly adds the the filter delay(filter order * 0.5) amount of zero values(29 in this case) to the end of the padded signal. - then it is passed to another builtin filter function with the coeffitcients retrieved from the opts variables - the output signal from the builtin filter function then has the filter delay amount of values removed from the front of the signal The logic was implimented in the code exactly as the logic above although was still not showing exact result and the reason was below. 1. Coefficients used in the builtin MATLAB filter() function was not the same as fir_51.mat file in Daryl's project. I found the actual coefficients used in the opts variable that was used in runtime within the lowpass() builtin function. 59 was the number of coefficients that was actually used and the values were also different. 2. The filter order != number of coefficients, but was filter order == number of coefficients - 1, which was 29 in this case 3. the buffering logic of Daryl's MATLAB code had a error, because matlab does not use 0 indexing, the buffer size was set to 1000 but the buffer was processing 1001 signals in everytime except the first buffer.
high pass filtering functionality | 2025-03-14 | logic of the high pass filter was not the same with the low pass filter. It was as below. 1. Daryls code layer - padding was 50 front and back, not like 60 in the low pass filter - pass on to MATLAB built in conv() function with padded signal and coefficients(which was imported from fir_51.mat file in the project) 2. Matlab Layer - the conv function just did a 1d convolution with the signal samples and coeffs. The conv function adds 50 samples to the signal length, which seems to be how convolution works. Logic was simple so was easy and straight forward so simple to recreate. Although I am curious on why the logic was different in both filterings. According to the full report, both just used fir filtering and didnt mention different paddings and post signal zero padding and pre removal were used. I wonder if this is why some misdetections and glitches
Artifact Detection | 2025-03-17 | The detecting artifact logic is simple, just getting the highest value that is over the threashold, which is a static value. This is concerning. Larrisa's full report mentiones(page9) that the threshold must be manually tuned for each patients as the amplitude of the pacing artifacts varied in defferent datasets.
NEO Transform | 2025-03-18 | The NEO transform in the MATLAB code works as follows. - creates a array of 1s - assigns the Neo transform output value starting the 2nd index of the array(which means the 1st index is still 1) While recreating the NEO transform functionality, ran in to memory errors. Found out that the MATLAB's NEO transform function output [input -1] values. Investigated this and look like it is common in NEO transforms due to how it is calculated. The values that was removed in the output was the last value, which is 1.
Moving Average Filtering | 2025-03-18 | Incountered unmatching result while creating this, where the reason was due to skiping of 1st index value during the calculation. This is connected to The adding of 1 in front of the output signals in NEO transform. If NEO transform later gets rid of the 1 value in the front of the signal, this may need to be fixed with it.(moving_average_filtering function in activation_detection.c)