## Progress
Plan | Functionality |  | Task | Summary | Description | Est Start | Start Date | End Date | Status | Notes
Step 3 - Recreate the MATLAB project with C without using any libraries as possible and run it on desktop(goal is to make it run on a PC or similar level real time processor so need to be as light and simple as possible) | Initial env prep | Project Setup |  |  |  |  | 2025-02-20 | 2025-02-20 | done
| Data Initialization | Data Import and Initialization | Import file |  |  |  | 2025-02-20 | 2025-02-21 | done
|  |  | Channel signal retrieval |  |  |  | 2025-02-28 | 2025-02-28 | done
|  |  | Downsampling |  |  |  | 2025-02-21 | 2025-03-02 | done
|  | Result Compare | Save read data to csv(MATLAB) |  | Save data in each step |  | 2025-02-21 | 2025-02-21 | done
|  |  | Compare Data | compare with imported file data for testing | Test the C program by comparing result of MATLAB and C program, throw error when not the same |  | 2025-02-21 | 2025-02-21 | done
| Preprocessing Stage | Preprocessing | Low-Pass & High-Pass Filtering | Remove noise while preserving slow waves. | Removes high-frequency noise and baseline drift. Uses FIR filters for smooth processing. | 2025-03-03 | 2025-03-03 | 2025-03-14 | done | May need to adjust later. Currently copied wrong logic in Daryl's project to get same results. Also the result have a average difference of 3.64e-11 compared to the daryl's results. Largest diffence was 1e-8. PERCISION constant of PRECISION to 1e-8 was set to check the difference of MATLAB and C output. if difference is greated that PRECISION, error will occur
|  |  | Artifact Detection & Removal | Clean the signal from artificial stimulation effects. | artifact_detect.m: Detects artifacts by finding extreme values. artifact_remove.m: Removes detected artifacts and replaces them with cubic spline interpolation. | 2025-03-06 | 2025-03-14 | 2025-03-18 | done | Changed PRECISION to 1e-7 because the max diff between matlab and C increased
| Feature Extraction | Detection | Non-Linear Energy Operator (NEO) | Highlight activation points. | Enhances sudden energy changes in the signal. Helps detect slow wave activations. | 2025-03-10 | 2025-03-18 | 2025-03-18 | done | Changed PRECISION to 1e-6 because the max diff between matlab and C increased. Odd implimentations in MATLAB code which was mirrored in the C code
|  |  | Max Average Filtering |  |  |  | 2025-03-18 | 2025-03-18 | done
|  |  | Edge Detection | Enhance slow wave activation points. | Detects sharp drops in the signal (which correspond to slow wave activations). Uses a convolution kernel [1, 0, -1] to find steep slopes. | 2025-03-13 | 2025-03-18 | 2025-03-20 | done | Odd implimentations of skiping the first sample of the filtered signal during conv encountered in the MATLAB code. Seems to be connected with the odd implimentation in the neo transform
| Activation Detection | Thresholding | Thresholding | Detect valid slow wave activations while ignoring noise. | A dynamic threshold is used to mark slow wave activations. | 2025-03-17 | 2025-03-20 | 2025-03-20 | done
| Post-Processing |  | Duplicate Removal | Ensure one activation per cycle. | Removes duplicate detections within 500 samples (since slow waves are ~20 sec apart). Prevents false positives due to signal fluctuations. | 2025-03-20 | 2025-03-24 | 2025-03-24 | done
| Testing and Refactoring | Testing and Refatoring |  |  |  | 2025-03-24 | 2025-03-24 | 2025-03-26 | done
Step 4 - connect gut model to C Prog | Simulink to C | Research & Review |  |  |  | 2025-05-01 | 2025-05-01 | 2025-05-02 | done
|  | Implementation |  |  |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | done | Implemented TCP server in C program
| Dataset simulation | Dataset simulink model |  |  |  | 2025-05-06 | 2025-05-03 | 2025-05-04 | done | Create a Simulink model that sends samples from a dataset file to a C TCP server via TCP/IP at the original (real-time) sampling rate.
| Circular buffer implementation | Create circular buffer |  |  |  |  | 2025-05-05 | 2025-05-05 | done
|  | Apply circular buffer into c program |  |  |  |  | 2025-05-06 | 2025-05-14 | done | Need to implement concurrency. Signal reception and signal processing should be executed in separate threads to ensure that incoming samples are not missed during processing.
| Multithreading for signal reception and detection pipeline | Implement threads |  |  |  |  | 2025-05-14 | 2025-05-14 | done
|  | Condition vars implementation for process thread |  |  |  |  | 2025-05-14 | 2025-05-16 | done
|  | Pipeline modification for new implementation |  |  |  | 2025-05-19 | 2025-05-19 |  | done
|  | refactoring | [5 empty] | 2025-05-28 | done
| Use gut model |  |  |  |  | 2025-05-07 | 2025-05-28 |  | pending
Step 5 - Migrate to ARM Processor | Initial env prep for DE1-Soc |  |  |  |  | 2025-05-15 | 2025-05-28 | 2025-05-29 | done
| Migrate C prog to board |  |  |  |  | 2025-05-19 | 2025-05-29 | 2025-05-29 | done
| Link PC(Simulink) to Board(C program) |  |  |  |  | 2025-05-26
| Implement pacing feature in PC |  |  |  |  | 2025-06-02
| Migrate pacing functionality to board |  |  |  |  | 2025-06-09
Step 5 - Migrate to FlexPRET | Initial bare metal dev env prep |  |  |  |  | 2025-06-16
| Migrate C prog to FlexPRET env |  |  |  |  | 2025-06-23
| Link PC(Simulink) to FlexPRET |  |  |  |  | 2025-06-30
Step 6 - Testing and Optimization | [5 empty] | 2025-07-07

## Journal
Low Pass Filtering functionality in C | 2025-03-07 | It took alot of time attempting to understand the filtering logic, especially due to Daryl's MATLAB project used a built in MATLAB lowpass function. It was not clear what coefficient was used in this function, but there was a file called lowpass_coeffs.mat in the root directory of the project, but was not imported in any part of the project code. I assumed somehow it was an extracted coefficient of the whats used in the lowpass function so used is in my C low pass filtering functionality. I got a similar trend of result comparing with the matlab code(shown in diagram, but C showing results of about 150 higher that the MATLAB results. | #VALUE!
|  | I got it to get similar result but not exactly the same. I think it may be because I am using floats instead of double in my C code, Matlab uses double. Plan to change to double next | #VALUE!
| 2025-03-12 | Figured out the problem from deeply investigating the daryl's MATLAB project's lowpass filter logic and reading documentations of how the built in filter() function works. Found out the following. 1. In Daryl's code layer - 60 padding front and back added to signal(first value for front 60 values and end value for back 60 values) - then it is passed to built in lowpass function - then the paddings are removed front and back from the output signal from the lowpass function 2. MATLAB Layer - built in lowpass function checks the opts variables and runs FIR logic, which firstly adds the the filter delay(filter order * 0.5) amount of zero values(29 in this case) to the end of the padded signal. - then it is passed to another builtin filter function with the coeffitcients retrieved from the opts variables - the output signal from the builtin filter function then has the filter delay amount of values removed from the front of the signal The logic was implimented in the code exactly as the logic above although was still not showing exact result and the reason was below. 1. Coefficients used in the builtin MATLAB filter() function was not the same as fir_51.mat file in Daryl's project. I found the actual coefficients used in the opts variable that was used in runtime within the lowpass() builtin function. 59 was the number of coefficients that was actually used and the values were also different. 2. The filter order != number of coefficients, but was filter order == number of coefficients - 1, which was 29 in this case 3. the buffering logic of Daryl's MATLAB code had a error, because matlab does not use 0 indexing, the buffer size was set to 1000 but the buffer was processing 1001 signals in everytime except the first buffer. I have set the BUFFER_SIZE constant to 1001 in the C program to mirror the outcome.
high pass filtering functionality | 2025-03-14 | logic of the high pass filter was not the same with the low pass filter. It was as below. 1. Daryls code layer - padding was 50 front and back, not like 60 in the low pass filter - pass on to MATLAB built in conv() function with padded signal and coefficients(which was imported from fir_51.mat file in the project) 2. Matlab Layer - the conv function just did a 1d convolution with the signal samples and coeffs. The conv function adds 50 samples to the signal length, which seems to be how convolution works. Logic was simple so was easy and straight forward so simple to recreate. Although I am curious on why the logic was different in both filterings. According to the full report, both just used fir filtering and didnt mention different paddings and post signal zero padding and pre removal were used. I wonder if this is why some misdetections and glitches
Artifact Detection | 2025-03-17 | The detecting artifact logic is simple, just getting the highest value that is over the threashold, which is a static value. This is concerning. Larrisa's full report mentiones(page9) that the threshold must be manually tuned for each patients as the amplitude of the pacing artifacts varied in defferent datasets.
| 2025-05-21 | There is a condition check for removing artifact when calling remove_artifact fucntion in the c program where I commented out better implementation and just used a Matlab prog mimiced one. if (x2 < ARTIFACT_DETECT_WINDOW_WIDTH && x1 >= 0) // this make sence but it is not the same as MATLAB logic // if (x2 < ARTIFACT_DETECT_WINDOW_WIDTH && x1 >= 2) // this mimics the MATLAB logic Need to change in the future if need to refactor
NEO Transform | 2025-03-18 | The NEO transform in the MATLAB code works as follows. - creates a array of 1s - assigns the Neo transform output value starting the 2nd index of the array(which means the 1st index is still 1) While recreating the NEO transform functionality, ran in to memory errors. Found out that the MATLAB's NEO transform function output [input -1] values. Investigated this and look like it is common in NEO transforms due to how it is calculated. The values that was removed in the output was the last value, which is 1. refer to neo_transform function in detection.c
Moving Average Filtering | 2025-03-18 | Encountered unmatching result while creating this, where the reason was due to skipping of 1st index value during the calculation. This is connected to The adding of one value of 1 in front of the output signals in NEO transform. If NEO transform later gets rid of the 1 value in the front of the signal post its operations before it outputs result, this may need to be fixed with it.(moving_average_filtering function in activation_detection.c). The full reports did not specifically mention what the moving average filtering was for and how the calculations were done so solely relied of mirroring the moving_average_1s_window function that was used in the MATLAB project. Therefore, I am not sure if there was a mistake in the logic or everything was intentional. Mentions of it in Daryl's report page 15 and Larissa's report page10.
Edge Detection | 2025-03-20 | Logic of alg of edge detection is as below. 1. convolve the artifact removed(before neo transformed) signal and kernel of [-1, 0, 1] 2. convolve the output of step 1 and the neo filtered(after maf) signal 3. negative values in the output of step 2, is set to 0, and all the positive values are set to the squared value of itself 4. get the mean of output of step 3 and set all the values of output of 3, that are less than the mean value to 0 Ran into some issues during creating this in C due to step 2. In this stage the output of step one is 1 signal larger that the neo filtered signal which seems to be a connected issue from the neo transfrom stage. In the matlab code to solve this, it seems the first value of the convolved signal is skipped the conv of step 2. These signals maybe not relevant since they are few values that are in the front and end of the buffer, but I worry these small differences building up create bigger issue in the activation detection.
Testing & Refactoring | 2025-03-26 | After finishing activation detection functionality, I've encountered that the good signal datasets were not outputting same results as the MATLAB project. I've been testing with the bad signal datasets only to check the c program outputs during the recreation process. After long investigation, I found the below was the issue. 1. Good signal datasets had opposite orientation(channel = row, samples=col) 2. The MATLAB's built-in lowpass function used in the MATLAB project was dynamically creating the coefficents used in the filtering process This means that the C lowpass functionality also needs to create coeffs dynamically too. I still have to analyse how it does it and what component is uses for the calulations(sample freq, signal length, etc).
Luman Wang's Thesis Chap 5 Review | 2025-03-27 | I realized after reviewing the pacing algorithm in Dr. Wang's thesis. The MATLAB program was designed to just verify that it filters the data well enough to detect activations from the datasets, which is why it just import the whole dataset file, then buffering through it, then showing result of all the detected activations, then program ends. In order to implement the pacing correction features to the program, it needs process the signals in a frequency as it would in real life, so that I can eventually test the pacing feature if it reacts well according to the state changes. But then again, I may be thinking too much like a industry software engineer. Thinking that the goal of this research is to validate that this program is a valid method, this means that showing results via diagrams and graphs as evidence that this method is valid is the goal here. Maybe modifying the code to actually work in real time is like it would in a real environment is for future work? Then if so, to think like a researcher, the main question I should be asking is, How can the pacing functionality be created for the purpose to validate it is correctly working, not to pace the actual GI track?
| 2025-03-27 | There was another possible flaw with the signal processing of Daryl and Larissa's project that I realized after realizing the above. From what I understand, the signal processes in buffers of 1000 samples, which is 31.25 seconds at 32 Hz, and slides forward by 500 samples each time, giving a 50% overlap. Here's my concern: Let’s say the real-time gut signal is coming in continuously. Firstly, 31.25 seconds over the normal activation time of 3cpm(every 20 secs), meaning that, in normal activation scenario, the program will detect an activation after at least 11.25 secs after the next activation of the the actual activation has occurs. Is this right...? More over, when processing Buffer A, it takes 31.25 seconds to fill it. We have the 50%(500 samples) overlap, to validate activations near the end of Buffer A which I understand. That means we’re effectively delaying reliable detection of Buffer A’s end activations until Buffer B completes — another 31.25 seconds later. So overall, wouldn’t this introduce a minimum latency of over 60 seconds (31.25 + 31.25) before we can respond to certain activation events? A abnormal activation will be detected over a minute later then start pacing. A corrected activation will only be detected after over a minute later, then the pacing will stop. Is that or isn't that too slow real time closed-loop GES? Has this been considered in Daryl's and Larissa's project? I will need to clarify this with Daryl if I have correctly understood it am not missing anything, after clarify with Dr Malik and Dr Wang about it. If this is an issue, i may need to lower buffer to a realistic value, but I am not sure how much process I may need to go through to validate the results, which I personally am not exited about. In the mean time, I will start with the next stage.
| 2025-03-27 | I realized that the worst case senario of the above mentioned is wrong. If you think about it, all initial activations detections will be in the last half of the buffer. For example, if there was a activation detections in the first half of the buffer, it means that, that half's samples were already transmitted in to the past buffer, meaning it as already been detected. So taking only the last buffer in to account, worst case senario would be if the activations was in the first sample of the last half of the buffer. For it to be initially detected, it would take half the buffer length samples to be transmitted(31.25/2 secs) to start processing the buffer. And the activation detection feature detects it to be a possible detection and then wait for the next buffer to validate it since it will be in the start of the buffer. (Does it have to wait for the next buffer? if it is in the starting edge of the signal, maybe the prior buffer is a more reliable source? Needs to be investigated.) The next buffer starts after 500 samples from the prior buffer(another 31.25/2 secs), which means duration of 1000 samples of delay is the worse case.
| 2025-03-27 | After thinking of the above, I realized the activation state change conditions are not set at the moment, meaning I have to set the conditions. If the conditions of changing to a normal activation is to only change state if activation was detected in the middle 500 samples of the buffer and wait for the next buffer if it was detected in the end of the buffer, this would reduce the worst case delay to about around 23.44 secs, which will be a scenario where activation signal was in the just after the middle 500 samples, or in other words, the start of the last quarter of the buffer.
| 2025-03-31 | Ive discussed with daryl regarding the buffer window size, the delay and the half buffer sample overlap. I realized that I have been approaching the role of the overlap wrong. I thought for some reason that it was to verify the activation that was in the last half of the buffer. Its partially correct, since if the activation was detected in the last buffer, it wouldnt need verification, it would mean that it detected a activation which needs not verifying. Incase the buffer couldnt detect the activation due to being in the end of the buffer and then it would most definately be detected in the next buffer, since the activation would have been in the end of the first half of the buffer, hence being in the center of the buffer window. Also I now see why the 1000 sample(31.25s) window makes sense. one whole slow wave signal is around 20s. And for the buffers to have the whole signal in it, 1000 samples seem like a good number and the overlap would make it that a slow wave would be within the center of the window if it wasnt on the previous buffer window. And even if the signal was in the edge of the windows, since the part that is essential to activation detection is around only 8s(ave 12 s resting phase), if the first half was is in the buffer window, it will most likely be detected. Thus, the worst case senario would be if the activation occured after #750 sample in the buffer window. that would be (31.25 x 0.25) + (31.25 0.5)s delay since it will be detected in the next buffer window, which is still around 23.44s, but having the activation signal in the start of the slow wave would make it more likely to be detected in the first buffer window. Hence it would most likely that delay would be less than 20 sec. Although I might have to check if this is okey with Dr. Malik.
| 2025-03-31 | Met with Dr Malik, more confused. I don’t know if my explaination was the issue, but got advice that I might need to modify the algorhythm to a double buffering method, which I have no clue about. I didn’t even know what type of buffering the current method was. Need to do more research about this concepts. Also was told that i donot need to test the datasets on desktop, but just connect it to the gut model instead using simulink. I have to learn what simulink does to understand what this means.
| 2025-04-18 | Due to mid sem break, and personal matters, and Luman's delay in sharing gut model, pacing alg, was not able to make any progress. Also, I found out that the part 4 students project was not producing same outputs as the algorithm results they have provided in their compendium. I communicated with Daryl and he said the thresholds and some other components were asjusted for the good datasets and bad datasets, which seems to be an unfinished version of the algorithm. I get into a delema about if I should spend time fixing the alg, so requested to meet with my supervisor to get some advice.
| 2025-04-23 | Meeting with the supervisor certainly cleared my mind. I was worried that I would not get to the hardware implementation part of the research if I had to work on the signal processing alg. But Dr Malik has advised that my research focus should be on the hardware implemenatation since it is a embedded system research topic, not a signal processing for gut pacemaker. My goal should be implementing the alg into to a embedded system, even though the alg doesnt work perfectly. The optimization for gut signal processing can be part of another project, but doesnt nessesarily have to be part of this one. This definately cleared my mind and a clear pathway. Will proceed to next step.
Apply circular buffer into c program | 2025-05-06 | Upon doing this, I realized that without concurrency implemented here, if the activation detection pipeline process takes longer than the interval between each sample being sent from Simulink, incoming samples will not be received in time, or the server would miss incoming samples due to blocking, leading to data loss. So to address this, the receiving(reception, and the processing task must be decoupled and executed concurrently. The reception of signal will be handled in the main thread and the pipeline in the second thread. Although, the signal processing pipeline only takes about 0.15ms to complete and assuming the samples are transmitting in around 32 hz, which is about 30ms interval for each transmission, the processing complete within the before the next transmission where the server can start waiting for the next sample before the next transmission. But Im not sure how long the pipeline would take in a restricted environment, thus feel that it is better to implement this now than later.
Simulink to C Communication Implementation & Multithreading | 2025-05-17 | After completing the multithreading implementation for signal reception and the activation detection (signal processing) pipeline, a few concerns came to mind: 1. pthread cannot be used for multitasking in bare-metal programming environments. 2. TCP/IP is also unavailable in bare-metal environments. To make future transitions smoother—particularly toward embedded platforms and eventually FlexPRET—I decided to abstract both the multithreading and communication interfaces. This way, I can adapt the underlying implementation for each new environment without changing the core application logic.
Gut Model connection to C program | 2025-05-28 | While analysing Luman's repo that she shared, I found that the gut model was not modularised and just in the simulink file with pacing blocks and other components. I'm having difficulty understanding and analysing it, since the implementations in it are not really clear. I requested to meet Luman again to get her to explain what each block is in the simulink model, so that I can just extract the actual gut model and modularize it. So this part will be pending until I meet Luman. In the meantime, I will just go on and start the migration process to the DE1 SoC board.
Migrate C prog to DE1SoC board | 2025-05-29 | I had trouble getting the crosscompiled file to run successfully on the board. I needed extensive assistance from chatGPT to figure out how to solve the issue. Basically it was 3 things. 1. version of the toolchain, where I handled by extracting the root file system fromthe board and recomplied with --sysroot pointing to the rootfs 2. Then i found that the there were missing headers and libs in this root file system so copied the missing files from the compiler to the root file 3. and there was linker error for pthead functions so added -lpthread to the compile command which caused /lib/libc.so.6: version `GLIBC_2.17' not found and solved that my adding --static to the comple command this took a long time with chatgpt and without it, im not sure how long it would have taken. I found that there is a rootsys that I can download from the site i downloaded the toolchain. I wil try to complile again with that instead.

## README
how to configure the makefile for de1-soc ARM Linux compiler | in notion | Pacemaker Dev Notes: Cross-Compiling for DE1-SoC ARM Linux